## Slide 1: TIM 58 Finishing Ch 2: Project Management

## Slide 2: Project Effort Estimation
Estimation involves trade-offs between functionality, time and cost
It is the process of assigning projected values for time and effort
Most accurate estimates come from experience
Use-case point method; based on:
  Technical complexity factors (13)
  Environmental factors (8)

## Slide 3: Use-case Estimation Example
Actors & Use-cases:

## Slide 4: Use-case Estimation Example
Technical complexity factors:

## Slide 5: Use-case Estimation Example
Environmental factors & final estimate:

## Slide 6: Creating & Managing the Workplan
Workplan: a dynamic and sequential list of all tasks needed to complete a project
Approaches:
  Modify existing or completed projects
  Derive the tasks from the methodology in Fig 2-17, 2-18.
Unified Process:
  Iterative & incremental
  Workplan is also iterative & incremental
    Tasks and time intervals follow the phases
    Different tasks executed for each workflow

## Slide 7: Evolutionary Work Breakdown Structures
Organized in a standard manner across all projects
Created in an incremental & iterative manner
Generality supports learning from past mistakes and successes
Unified Process:
  Workflows are the major divisions
  Workflows are decomposed along the phases
  Phases are decomposed along the required tasks
  Tasks are added as each iteration is completed

## Slide 8: Scope Management
Scope “creep”
  Occurs after the project is underway
  Results from adding new requirements to the project
  Can have a deleterious effect on the schedule
Techniques to manage the project scope:
  Identify all requirements at the outset
  Allow only those changes deemed absolutely necessary
  Carefully examine the impact of suggested changes
  Delay some changes for “future enhancements”
  Time boxing
Notes: Timeboxing is a technique that is used to organize a project when time is a critical issue. With timeboxing, a fixed deadline is established, and the project team prioritizes the functionality of the system so that the essential features are delivered within the set deadline. If some features must be omitted given that time frame, they are postponed to a later version of the system. With this technique, the users are assured of getting a system with essential functionality by the project deadline, and other, less essential features and refinements are added in later system versions

## Slide 9: Staffing the Project
Goals:
  Determine how many people are required
  Match skill sets to required activities
  Motivate the team to meet the objectives
  Minimize conflicts

## Slide 10: Motivating People
Motivation is the greatest influence on performance
Monetary rewards usually do not motivate
Suggested motivating techniques:
  20% time rule
  Peer-to-peer recognition awards
  Team ownership (refer to the team as “we”)
  Allow members to focus on what interests them
  Utilize equitable compensation
  Encourage group ownership
  Provide for autonomy, but trust the team to deliver

## Slide 11: Creating a “Jelled” Team
A team of people so strongly knit that the whole is greater than the sum of its parts
Characteristics of a jelled team:
  Very low turnover rate
  Strong sense of identity
  A feeling of eliteness
  Team vs. individual ownership of the project
  Team members enjoy their work

## Slide 12: Creating a “Jelled” Team
IN-CLASS DISCUSSION:
  HAVE YOU BEEN ON A SUCCESSFUL TEAM?
  HOW DO YOU ACHIEVE THIS?
Characteristics of a jelled team:
  Very low turnover rate
  Strong sense of identity
  A feeling of eliteness
  Team vs. individual ownership of the project
  Team members enjoy their work
Notes: Research has shown that technically oriented people are motivated by recognition, achievement, the work itself, responsibility, advancement, and the chance to learn new skills. The worst ways to motivate technical staff include setting unrealistic deadlines, failing to recognize good effort, accepting low quality output, rewarding all team members monetarily regardless of work quality, failing to include team members in important project decisions, and providing poor working conditions.

## Slide 13: The Staffing Plan
Calculate the number of people needed:
Pay attention to technical and interpersonal skills
Lines of communication increase exponentially as people are added to a project
Create a reporting structure for projects with large numbers of people assigned
Form sub-teams as necessary
Assign the Project Manager, Functional lead & Technical lead

## Slide 14: Handling Conflict
Preventing or mitigating conflict:
  Cohesiveness has the greatest effect
  Clearly defining roles and holding team members accountable
  Establish work & communications rules in the project charter
Additional techniques:
  Clearly define plans for the project
  Make sure the team understands the importance of the project
  Develop detailed operating procedures
  Develop a project charter
  Develop a schedule of commitments in advance
  Forecast other priorities and their impact on the project

## Slide 15: Environment & Infrastructure Management
Environment—Choose the right set of tools
  Use appropriate CASE tools to:
    Increase productivity and centralize information (repository)
    Utilize diagrams—more easily understood
  Establish standards to reduce complexity
Infrastructure—Document the project appropriately
  Store deliverables & communications in a project binder
  Use Unified Process standard documents
  Don’t put off documentation to the last minute

## Slide 16: Staffing the Project
Deliverable—The staffing plan, which includes:
  Number & kind of people assigned
  Overall reporting structure
  The project charter (describes the project’s objectives and rules)